## Sheet1
Sprint Backlog
User Story | Tasks | Original Estimate | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Sprint Review
As a User I want to login to the system so that I can use the system | System Analysis | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| Database Designer | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75
| Web Designer | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| Programmer | 6 | 4 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| Tester | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
As a Student I want to submit EC claims so that I can inform to EC Coordinator about my cercumstance | System Analysis | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75
| Database Designer | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25
| Web Designer | 5 | 0 | 2 | 3.5 | 0 | 0 | 0 | 0 | 0 | 1
| Programmer | 8 | 0 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 1
| Tester | 3 | 0 | 0 | 2.5 | 1 | 0 | 0 | 0 | 0 | 0
As a Student I want to submit claim with upload evidence so that I can prove the claim to the coordinator. | System Analysis | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
| Database Designer | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Web Designer | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Programmer | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0.5
| Tester | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0.5
As an EC Coordinator I want to receive email when student submit claim so that I can able to know about the claim | System Analysis | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| Database Designer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Web Designer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Programmer | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0.5
| Tester | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0.75
As an EC Coordinator I want to processed any calim within 14 days so that I can examine the claim | System Analysis | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75
| Database Designer | 5 | 0 | 1 | 4.5 | 0 | 0 | 0 | 0 | 0 | 1
| Web Designer | 6 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 1
| Programmer | 4 | 0 | 0 | 0 | 0 | 4.5 | 0 | 0 | 0 | 1
| Tester | 5 | 0 | 0 | 0 | 0 | 3 | 1.5 | 1 | 0 | 0
As a Student I want to get email when my claim is processed so that I can get notify about my claim | System Analysis | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Database Designer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Web Designer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Programmer | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0.5
| Tester | 3 | 0 | 0 | 0 | 0 | 3.5 | 0 | 0 | 0 | 0.5
As an EC Manager I want to view all claims so that I can oversee the processes | System Analysis | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
| Database Designer | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Web Designer | 4 | 0 | 0 | 2 | 2 | 0 | 3 | 0 | 0 | 0.75
| Programmer | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
| Tester | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0.25
As an Administrator I want to view or edit any data such as claim, evidence, role, add module or batch and reset user passwords so that I can maintain the system | System Analysis | 7 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 1.5
| Database Designer | 8 | 0 | 4 | 1 | 3 | 0 | 0 | 0 | 0 | 1
| Web Designer | 6 | 0 | 0 | 3 | 2 | 1.5 | 0 | 0 | 0 | 1
| Programmer | 10 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 1 | 2
| Tester | 8 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4 | 1
As a Student I want to access my own claims and profile so that I can edit or updatre my claims and view profile | System Analysis | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Database Designer | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Web Designer | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| Programmer | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0.5
| Tester | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0.5
As an Admin/EC Manager I want to view statistical reports so that I can understand the claim processes | System Analysis | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1
| Database Designer | 5 | 0 | 0 | 3 | 3 | 1 | 5 | 0 | 1 | 0
| Web Designer | 3 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
| Programmer | 4 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0.5
| Tester | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0.5
As an Admin/ EC Manager I want to view exceptional reports so that I can understand the claim processes | System Analysis | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 1
| Database Designer | 5 | 0 | 0 | 2 | 3 | 1 | 0 | 0 | 0 | 0.75
| Web Designer | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0.75
| Programmer | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0.5
| Tester | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0.5
Total |  | 200 | 15 | 47.5 | 39.5 | 35 | 20.5 | 37.5 | 15 | 13 | 30.25
[7 empty] | Total Worked Hours |  |  | 223